## Sprint 3-1-26 ¦ 3-14-26
Finished Date | Create Date | Started Date | On Hold Date | Re-Started Date | Assignation Date | Label | Estimation | Completed | Non Workable Days | Real Worked time | Difference est and real | Assigned By | Dev | Project | Jira Ticket Number | Ticket Name | Resolution Details | Status | Effort Comments
2026-03-06 13:03 | 2026-02-27 13:53 | 2026-03-02 | 2026-03-03 |  | 2026-03-02 | CurrentVersion | 12 |  | 0 |  |  | Adrian Rojas | Adrian Rojas | MFGR10 - MFGROW - Deacom | MFGR10-43562 | Dev 1 - MFGR10-43561 - SR- Print destinations not working in WMS | Waiting for PC to give examples to reproduce the steps. | Done
2026-03-06 15:38 | 2026-03-03 11:53 | 2026-03-03 | 2026-03-03 | 2026-03-04 | 2026-03-03 | DEV | 12 |  | 0 |  |  | Adrian Rojas | Adrian Rojas | MFGR10 - MFGROW - Deacom | MFGR10-43726 | Exec 1 - MFGR10-43725 - SR- Incorrect GL Postings with Un-Finish | Paused research for PTO, will continue on friday march 4th. | Done
2026-03-13 13:59 | 2025-02-27 07:55 | 2026-03-09 | 2026-03-09 | 2026-03-12 | 2026-03-09 | DEV | 24 |  | 0 |  |  | Adrian Rojas | Adrian Rojas | MFGR10 - MFGROW - Deacom | MFGR10-10167 | Dev 1 - MFGR10-9124 - Customer Print Statements - Page is loading endlessly when previously it loaded quickly |  | Done
2026-03-13 07:52 | 2026-03-09 11:42 | 2026-03-09 | 2026-03-10 |  | 2026-03-09 | DEV | 12 |  | 0 |  |  | Adrian Rojas | Adrian Rojas | MFGR10 - MFGROW - Deacom | MFGR10-44072 | Dev 1 - MFGR10-44071 - 17.03.010.0003 dbo.dxdflt updater error | Inmediate workaround. To unblock the QA environment right now (without a code fix): There is a row in dxdflt — with empty/NULL data — causing the ALTER TABLE ALTER COLUMN df_somrpfacility nvarchar(30) NOT NULL to fail because that row had NULL in the original column state. Delete this row with DELETE FROM dxdflt WHERE df_id = 2; Then re-run the updater. I will add a guard in the updater that will fix this issue. This would be available in next build release. | Done
2026-03-13 09:48 | 2026-03-10 09:40 | 2026-03-11 | 2026-03-11 |  | 2026-03-10 | DEV | 16 |  | 0 |  |  | David Suarez | Adrian Rojas | MFGR10 - MFGROW - Deacom | MFGR10-44095 | Dev 1 - MFGR10-44093 - SR- Henry Broch - Copy QC Group on Receipt Throws Error - 04364454 |  | Done
2026-03-05 06:21 | 2026-02-27 09:44 | 2026-03-02 |  |  | 2026-03-02 | DEV | 0 |  | 0 |  |  | Cristian Guzman Villca | Cristian Guzman Villca | MFGR10 - MFGROW - Deacom | MFGR10-43543 | Dev 1 - MFGR10-43537 - Misaligned prompt on form invout |  | Done
2026-03-10 09:26 | 2025-12-03 14:42 | 2026-03-06 |  |  | 2026-03-06 | DEV | 12 |  | 0 |  |  | Cristian Guzman Villca | Cristian Guzman Villca | MFGR10 - MFGROW - Deacom | MFGR10-36493 | Exec 1 - MFGR10-36492 - SR- Shipped ICT Inventory Doubling when Received at Facility |  | Done
2026-03-13 15:04 | 2026-03-10 09:26 | 2026-03-10 |  |  | 2026-03-10 | DEV | 12 |  | 0 |  |  | Cristian Guzman Villca | Cristian Guzman Villca | MFGR10 - MFGROW - Deacom | MFGR10-44089 | Dev 1 - MFGR10-36492 - SR- Shipped ICT Inventory Doubling when Received at Facility |  | Done
| 2026-01-14 16:26 | 2026-03-06 |  |  | 2026-03-05 | DEV | 40 |  | 0 |  |  | David Suarez | David Suarez | MFGR10 - MFGROW - Deacom | MFGR10-39644 | Dev 1 - MFGR10-39642 - SR- Re: ECI - Case: 04107623 Cash Flow Report Correction Assistance - Follow-up Question from Customer |  | In Progress
2026-03-10 09:47 | 2026-03-02 07:09 | 2026-03-02 | 2026-03-04 |  | 2026-03-02 | DEV | 24 |  | 0 |  |  | Henry Barboza | Henry Barboza | MFGR10 - MFGROW - Deacom | MFGR10-43578 | Dev 1 - MFGR10-43299 - SR- EDI 947 failure |  | Done
2026-03-09 10:32 | 2026-01-13 10:28 | 2026-03-04 | 2026-03-09 |  | 2026-03-04 | DEV | 40 |  | 0 |  |  | Jason McNeeley | Henry Barboza | MFGR10 - MFGROW - Deacom | MFGR10-39422 | Dev 1 - MFGR10-39421 - SR- Forecast vs Actuals in Forecast |  | Done
2026-03-10 15:48 | 2026-03-05 16:38 | 2026-03-09 | 2026-03-10 |  | 2026-03-09 | DEV | 12 |  | 0 |  |  | David Suarez | Henry Barboza | MFGR10 - MFGROW - Deacom | MFGR10-44054 | Exec 1 - MFGR10-44053 - SR- Morrison Lamothe: Morrison Lamothe: Financial statement issue |  | Done
| 2026-03-10 12:18 | 2026-03-10 |  |  | 2026-03-10 | CurrentVersion | 20 |  | 0 |  |  | Henry Barboza | Henry Barboza | MFGR10 - MFGROW - Deacom | MFGR10-44209 | Dev 1 - MFGR10-44208 - SR- Inventory Discrepancies when Receiving Transfers via WMS |  | In Progress
| 2026-02-19 12:12 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-09 | API | 24 |  | 0 |  |  | David Suarez | Jose Arcani | MFGR10 - MFGROW - Deacom | MFGR10-42726 | Dev 1 - MFGR10-42724 - CS AR - Invoices with Pre-Auth |  | In Progress
2026-03-09 13:10 | 2026-03-06 09:26 |  |  |  | 2026-03-06 | CurrentVersion | 0 |  | 0 |  |  | MFGROW Webhook | Rodrigo Alarcon Vargas | MFGR10 - MFGROW - Deacom | MFGR10-44056 | Dev 2 - MFGR10-42821 - SR- All Inventory moved by accident |  | Done
2026-03-06 07:47 | 2026-02-16 11:06 | 2026-03-02 |  |  | 2026-03-02 | DEV | 12 |  | 0 |  |  | Rodrigo Alarcon Vargas | Rodrigo Alarcon Vargas | MFGR10 - MFGROW - Deacom | MFGR10-42318 | Exec 1 - MFGR10-42317 - SR- DEV Request ¦ DSD ¦ Begin scoping for what it would take to have NET 1 Integrated with our DSD |  | Done
2026-03-11 15:35 | 2026-03-04 11:41 | 2026-03-11 |  |  | 2026-03-04 | DEV | 20 |  | 0 |  |  | David Suarez | Rodrigo Alarcon Vargas | MFGR10 - MFGROW - Deacom | MFGR10-43893 | Dev 1 - MFGR10-43892 - Chrome - User gets log out if a new browser tab is open with another Deacom connection |  | Done
| 2026-03-09 12:45 | 2026-03-09 | 2026-03-11 |  | 2026-03-09 | DEV | 16 |  | 0 |  |  | Rodrigo Alarcon Vargas | Rodrigo Alarcon Vargas | MFGR10 - MFGROW - Deacom | MFGR10-44078 | Dev 1 - MFGR10-44073 - “Inventory - allow move without source location” permission not enforced in WMS |  | To Do
| 2026-03-06 07:48 | 2026-03-06 | 2026-03-09 | 2026-03-11 | 2026-03-06 | DEV | 32 |  | 0 |  |  | Rodrigo Alarcon Vargas | Rodrigo Alarcon Vargas | MFGR10 - MFGROW - Deacom | MFGR10-44055 | Dev 1 - MFGR10-42317 - SR- DEV Request ¦ DSD ¦ Begin scoping for what it would take to have NET 1 Integrated with our DSD |  | In Progress